## Summary
Estimated Days
Admin Portal | Estimated No. of Days | 226.5
Web Portal | Estimated No. of Days | 107.5

## Admin Portal
Sr.No | Admin Portal Functionalities
1 | Category Management | Estimated No. of Days | Allocated Date Slot | Verification Points | Total No. of Asserts | Constraints (If any) | Verification Points Reviewed By | Person Working on Test Script | Status | Verification of Script Execution on Platform / Browser | Comments (if any)
Manage Category tab:
| Verify that 'Create' and 'Manage Category' tab is displayed. Verify the no of columns and sequence of column. Verfiy Activate/Inactivate button present under the grid. Verify that 2 buttons(Edit and Delete) are available in the grid for each category. Fields: Select,Position,Category Name,Category Type,Status,Action | 3 | W3 [27th July - 3rd August] | 1.Verifying duplicate Category creation validation. 2.Mandatory field validation on create page. 3. Verifying Inactivate and Activate Record Functionality. 4.Verifying all the column data present on manage page. 5.Verifying Delete button functionality. 6.Verifying Edit button functionality. 7.Position Changing functionality on manage page. 8.Category Name Validation. | 93 |  |  | Babban | Completed | IE11, Chrome & Firefox
| Click on Edit button to verify Edit category functionality. Verify fields on Edit Category screen. Edit the Category and modify values as required. Verify save and cancel button functionality on Edit category screen. Click on 'Delete' button to verify delete functionality. Verify access to content in web portal as per content selected in Admin Portal. | 3
Create tab:
| Click on Create tab to verify layout of Create tab screen. | 3
Create a category by entering, selecting values as required and clicking on Save button.
Verify if Category Name field is mandatory
Verify that positions is displayed correctly for all categories in the Category grid on Manage Category screen.
2 | Regional Access Management
Manage Regional Access tab
| Verify Columns :Select, Country Name, Access Type, Redirection Text, Redirection URL, Start Date, End Date, Notes, Status and Edit are displayed Verify default status in 'Status' column. Verify the functionality of Edit button. Verify the layout of Edit page. Verify the functionality of Save and Cancel button on Edit page. | 3 |  |  | 139
Create RegionTab:
| Click on Create Region Tab Verify Create Region screen layout. Verify All mandatory fields. Verify Country Name dropdown has list of all countries. Verify by default 'Redirection Text', 'Redirection URL' and End Date fields are disabled. Verify that By default Restricted radio button is selected. Enter Region details and click save button to create new region. Verify the functionality of Cancel button. Verify integration with WebPortal | 4
3 | Event Management
Event Management Landing page
| Verify the Event Management - Landing Page layout. Verify Search Events functionality: Search events should have following dropdown attributes: ID, Title, Location, Speaker. Verify Search field-User should be allowed to enter text in the search text field. Click on search Button-System should displays the associated results in a list below the search bar with the following columns: Title, Locations, Created by, Edited By and Edit. Verify 'My Events' checkbox functionality. Verify the Sort By functionality Verify Event title should be a hyperlink. Click on event title from the result list. Verify that data is pre-populated. Verify the functionality of Publish, Save and Cancel buttons on Edit page. Verify All mandatory fields. Verify Newly updated event should be displayed correctly in 'Recent Events' section. Verify the functionality of edit button appearing on the 'Recent Events' grid. | 7
Add New event button
| Verify 'Add New Event' button functionality: Verify the layout of all the 6 tabs: 1. Basic Information 2. Locations 3. Event Video and Timetable 4. Event Access Codes 5. Uploads 6. Event Price | 1.5
| Verify 'Basic Information' tab functionality. Verify 'Locations' tab functionality. Verify 'Event Video and Timetable' tab functionality: Two tabs-Selected Videos and Add Videos tab Verify 'Event Access Codes' tab functionality | 5
| Verify 'Uploads' tab functionality Verify 'Event Price' tab functionality. | 4
| Verify integration with webportal [Video Status] | 4
4 | Configuration Management
| Verify Columns:Key, Value, Action. Verify Configuration Management screen layout. Verify Save, Cancel and Edit button functionality. | 4
5 | Product Code Configuration
Manage Product Code
| Verify 'For Channels' section functionality Verify 'For Other Content Types' section functionality Verify Edit button functionality | 3
Create
Verify 'Content Type' dropdown Verify Save and Cancel button functionality Verify mandatory fields.
6 | CMS
CMS- Help
| Select CMS- Help menu dropdown. Verify layout of CMS screen. Modify text, Media file excluding video and button on particular screen by clicking on Edit button. Verify preview screen by clicking on preview button. Click on Save changes button and verify the change on web portal landing page. | 5
CMS- Services
| Select CMS- Services menu dropdown. Verify layout of CMS- services Modify text, image and button on Services by clicking on Edit button. Verify preview screen by clicking on preview button. Click on Save changes button and verify the change on web portal landing page. | 5
7 | Series Management
Manage Series
| Click on Manage Series tab. List of Series should be displayed. Verify 'My Series' section functionality. Verify grid fields: Select, Series Id, Series Name, Description, Created By, Edited By, Updated On, Status, Edit. Verify Reset button Functionality. Verify Activate/Inactivate button. verify the pagination functionality. | 3
Create Series
| Verify the layuot of the Create screen. Enter/select values as required on the Create screen and click on save button to create new Series. Verify functionality of 'Create Series' section. Verify functionality of 'Search' section. Verify functionality of 'Series Details' section. | 3
8 | User content management
Manage Contents Layout
| Verify the search functionality in "Manage content Verify the layout and tree structure of the Manage Content Screen. Verify the functionality of create button Verifythe functionality of Reject button. Verify pagination. | 5
9 | Individual Channel Pricing
Manage Channel Pricing for Individuals
| Verify the layout aof Select Channels Section. Verify Columns: Show, Channel Name ,Archive, Front, All. Fill all the required details and click on save button. | 3
10 | Manage Home Carousel
Home Carousel Configuration contents Layout
| Verify Video Title,Latest Video radio button and its functionality Verify Save and Cancel button Verify Integration with Webportal | 4
11 | Manage Channel Carousel
Channel Carousel Configuration Layout
| Verify Video Title,Latest Video radio button and its functionality Verify Save and Cancel button Verify Integration with Webportal | 4
12 | Reports
Access Report Layout
| Verify the layout of the Access Report Screen. Verify Mandatory fields. Verify the functionality of Clear And View Report buttons. Verify the details of the report containing details of all Activities. Verify the Pagination of the report. Verify the Clear button Functionality. Verify export to Excel, Word, PDF. | 5
Purchase Turn Away Report
| Verify the layout of thePurchase Turn Away Report Screen Fill all the details and verify its functionality Verify Clear And View Report buttons. Verify the details of the report containing details of all Activities. Verify the Pagination of the report. Verify the Clear button Functionality. Verify export to Excel, Word, PDF. | 5
Renewal Report Layout
| Verify the layout of the Renewal Report Screen Fill all the details and verify its functionality Verify Clear And View Report buttons. Verify the details of the report containing details of all Activities. Verify the Pagination of the report. Verify the Clear button Functionality. Verify export to Excel, Word, PDF. | 5
Sales and Revenue Report Layout
| Verify the layout of the Renewal Report Screen Fill all the details and verify its functionality Verify Clear And View Report buttons. Verify the details of the report containing details of all Activities. Verify the Pagination of the report. Verify the Clear button Functionality. Verify export to Excel, Word, PDF. | 5
Video Details Report Layout
| Verify the layout of the Renewal Report Screen Fill all the details and verify its functionality Verify Clear And View Report buttons. Verify the details of the report containing details of all Activities. Verify the Pagination of the report. Verify the Clear button Functionality. Verify export to Excel, Word, PDF. | 5
User Access Dashboard Layout
| Verify following field layout and functionaity 1 Select Account 2 Select User 3 Select Date 4 Select Activity 5 Select Device/Channel 6 Select Type of Video 7 Select Video Verify Continue button | 5
Video Admin Activity Report Layout
| Verify the layout of the Renewal Report Screen Fill all the details and verify its functionality Verify Clear And View Report buttons. Verify the details of the report containing details of all Activities. Verify the Pagination of the report. Verify the Clear button Functionality. Verify export to Excel, Word, PDF. | 5
Video By Channel Report Layout
| Verify the layout of the Renewal Report Screen Fill all the details and verify its functionality Verify Clear And View Report buttons. Verify the details of the report containing details of all Activities. Verify the Pagination of the report. Verify the Clear button Functionality. Verify export to Excel, Word, PDF. | 5
13 | Channel Management
Manage Channel Tab :
| Verify Two Tabs is displayed or not : Manage Channel and Create Channel Verify the no of columns and sequence of column. Field Name : Select, Position, Category, Channel Name, Channel Type, Status, Pricing Type, Access Type, Colour, Player, Watermark, Action. Verify Activate/Inactivate button present under the grid. Verify Content of Select Column, It should be checkboxes. Verify Content of Position column It should be dropdown. | 3 | W4 [4th August - 14th August] | 1.Verify Two Tabs is displayed or not : Manage Channel and Create Channel 2.Verify Activate/Inactivate button present under the grid. 3.Verify Content of Select Column, It should be checkboxes. 4.Verify Content of Position column It should be dropdown. 5.Verify Activate and Inactivate button functionality. 6.Verify the Channel Position functionality 7.Verify the Channel Edit Functionality 8.Verify the Delete functionality 9.Veriy the Create channel page UserInterface 10.Verify the Craete Page mandatory fields 11.Verify the Create Channel Functionality | 108 |  |  | Babban & Amit | Completed
| Select any record which is Inactive and click on Activate button and Verify Banner Message and value of 'Status' column, value of status column should be 'Active' also verify whether Edit button is displayed or not. Select any record which is Active and click on Inactivate button and Verify Banner Message and value of 'Status' column, value of status column should be 'Inactive' also verify whether Edit button is displayed or not. Verify Integration with Webportal | 1.5
| Change the position of any record and Verify the confirmation message is displayed or not. Click on No button and Verify the position of record, It should be old one. Change the position of any record and Verify the confirmation message is displayed or not. Click on Yes button and Verify the position of record, It should be updated one. Verify Integration with Webportal | 1.5
| Click on Edit button against any record and verify the that fields have pre-populated data. Fields should have repopulated data. Click on Edit button against any record and update the details of some fields and click on Cancel button. Verify that changes are not updated. Click on Edit button against any record and verify update the details of some fields and click on Save button. Verify that changes are updated. Verify Integration with Webportal | 4
| Click on Delete button against any record and Verify confirmation message is displayed or not. Click on Delete button against any record and click on No button of Confirmation message and verify whether the record is deleted or not. Click on Delete button against any record and click on Yes button of Confirmation message and verify whether the record is deleted or not. Verify that changes are updated. Verify Integration with Webportal | 1.5
Create Channel tab:
| Click on Create Channel tab to verify layout of Create Channel screen. | 5
Verify the messages for Mandatory fields.
Verify that, by default Black colour is selected in 'Channel colour' colour picker.
Verify the default option of 'Channel Type' drop down
Verify that each channel belong to respective category [Admin / Web portal]
Verify that newly created channel is displayed in 'Channel Grid' with correct details.
14 | Video Management
Video Landing Page :
| Verify the layout of Video Management -Landing Page. | 1.5
Search Videos Section :
| Verify that 'Search Videos' section is displayed on Video Management -Landing Page. | 4
Verify default selected attribute in 'Search Video' section.
Perform search functionality and Verify the Search result.
Verify video title in the result list it should be hyperlink.
Click on Title of any video and verify that it is navigated to Basic Information Page or not. Update some data and click on save button. Verify updates details is displayed or not.
Click on Edit button of any video and verify that it is navigated to Basic Information Page or not. Update some data and click on save button. Verify updates details is displayed or not.
Click on 'Comment' button for any video in the Video grid list and verify user is navigated to Comment Management screen or not.
| Verify Copy video funtionality. | 4
Recent Videos Section :
| Verify 'Recent Videos' section on Video Management -Landing Page. | 4
Verify 'Recent Videos' grid.
Verify recent videos details in the 'Recent Videos' grid.
Sort the record of 'Recent Video' grid and Verify the Sorted result.
Click on Title of any video and verify that it is navigated to Basic Information Page or not. Update some data and click on save button. Verify updates details is displayed or not.
Click on Edit button of any video and verify that it is navigated to Basic Information Page or not. Update some data and click on save button. Verify updates details is displayed or not.
Click on 'Comment' button for any video in the Video grid list and verify user is navigated to Comment Management screen or not.
| Verify Copy video funtionality. | 4
Basic Information Tab :
| Verify the sections displayed on Basic Information page. | 3
Verify whether Basic Info section is displayed by default.
Verify the layout of 'Basic Info' screen.
Verify that Video ID field is auto-populated.
Verify that inline error message are displayed for the mandatory fields for all section of Basic Information Tab (Pricing, Channel, Promotional Info, Copyright)
Verify whether the drop down for the selection of default channel is appearing as first field or not.
Verify whether a list of channels is appearing.
Verify whether each channel name is displayed with a check box to allow the user to select a channel.
Verify the layout of the 'Pricing' section. The 'Pricing' section should have two parts to the section: The first part should have three radio buttons at the top of the screen namely 1. Standard Channel Pricing 2. Free 3. Premium Second part should have: 1. A numeric text field called Price on Upload 2. Price after month-Two dropdowns and a numeric text box beside it. 3. A [+] button against each row.
Verify the layout of the 'Promotional Information' section.
Verify whether 'Use Default Image' radio button is selected by default.
Verify the state of the 'From Date' and 'Time' fields.
Verify the state of drop down appearing with Promo Video.
Verify the state of the browse button appearing with 'Promo Image' field.
Verify the layout of the 'Promotional Information' section.
Upload a file in 'Add Copyright' section and verify whether the details is added in grid or not.
Verify Email Address field is disabled or not.
Advance Tab :
| Verify Advance tab is second video. | 7
Verify that 'Location' section is displayed by default.
Verify the 'Location' section on 'Advance' tab.
Verify that inline error message are displayed for the mandatory fields for all section of Location Tab (Subtitle and subscription, Permission, Syndication, advert)
Enter all details and Click on save button and Verify that details added in the Location grid.
Verify details in Location grid
Click on Edit button and change the details and click on Reset button. 1. Verify data is pre populated after clicking on edit button. 2. Details of selected record is not updated in the grid. 3. After clicking on Cancel button all the fields get default mode.
Click on Edit button and change the details and click on Add button. 1. Verify data is pre populated after clicking on edit button. 2. Details of selected record should be updated in the grid. 3. After clicking on Cancel button all the fields get default mode.
Verify the functionality of Reset button.
Verify the delete functionality of Location record.
Verify 'Permission' section.
Create a Video Whose following attributes is selected in Permission section : - Disallow Download - Disable Comments - Disable Like/Dislike and Verify these functionality on web portal. All the selected functionality should be disabled.
Create a Video Whose following attributes is selected in Permission section : - Hide Record and Verify that video is displayed on web portal or not.
Verify the Layout of Thumbnail section.
create a video by uploading 'Thumbnail Image' and verify on Web Portal whether the selected image is displayed as a thumbnail or not.
Verify 'Subtitles' section.
Verify the default status of Language drop down, Browse button and Add button.
Click on 'Use Subtitle' Check box and check the status of Language drop down, Browse button and Add button.
Verify the inline error message is displayed or not.
Enter all details correctly and click on upload button and Verify that newly added record is displayed in the subtitle grid.
Verify download link is working or not
Verify Subtitle grid.
Check the status of Language drop down, Browse button and Add button under Transcript section
Enter all details correctly and click on upload button and Verify that newly added record is displayed in the Transcript grid.
Verify download link is working or not
Verify transcripts grid.
Verify details on 'Syndication' section. Syndication section should consist of a grid with the label as Use of Syndication followed by three rows with checkboxes namely Face book, YouTube and Linked.
Verify the 'Adverts' tab.
Advance Tab :
| Verify the Search functionality of Event Tab. | 1.5
Verify the layout of Selected Video section below the search section.
Keyword Tab :
| Verify the layout and functionality of Keyword Tab. | 1.5
Attachment Tab :
| Verify the layout and functionality of Attachment section. | 1.5
Verify the layout and functionality of Sponsor Details section.
Speaker Tab :
| Verify the Layout of Speaker page. | 4
Verify the layout and functionality of Create speaker tab
Verify created speaker is displayed in the selected speaker grid.
Verify the functionality to edit the speaker.
Verify the functionality to Search the speaker.
Client Tab :
| Verify the Layout of Create client Tab. | 3
Verify the functionality of Search section
Verify the functionality and Layout of creating new client.
Verify that created client is displayed on Manage Screen.
Verify the functionality to Edit the client.
Verify the functionality to delete the client.
Production Info Tab :
| Verify the layout of Production Info Tab. | 1.5
Verify the functionality of creating new production Info record.
Verify the functionality and Layout of creating new client.
Verify that created client is displayed in the below grid.
Verify the layout of grid.
Verify the functionality to Edit the Production Info detail
Verify the functionality to delete the Production Info detail
Upload Video Tab :
| Verify the layout and functionality of Upload Video section. | 3
Verify the layout and functionality of Preview video section.
Publish Tab :
| Verify layout and functionality of Publish Tab. | 4
Publish a premium video and verify layout and functionality on Web Portal
Publish a free video and verify layout and functionality on Web Portal
Publish a paid video and verify layout and functionality on Web Portal
Publish a video with Default Promo image and verify layout and functionality on Web Portal
Publish a video with selected Promo image and verify layout and functionality on Web Portal
Publish a video with Promo video and verify layout and functionality on Web Portal
Publish a video with countdown and verify layout and functionality on Web Portal
Verify save functionality of video record.
Verify creating a live video
15 | Comment Management
| Verify the two tabs appearing on Comment Management Screen: 1. 'Abuse filtration' 2. Comments Management | 5
Verify the layout of Abuse filtration tab.
Verify the functionality to add Abuse word in 'Abuse filtration' section.
Verify the functionality to add duplicate Abuse word in 'Abuse Filtration' tab.
Verify the functionality of Add Tag, Save and Reset buttons in 'Abuse Filtration' tab.
Verify that added abuse word is restricted on Web Portal.
Verify the layout of Comments Management tab.
Verify the functionality of Search video section.
Verify the functionality of My Videos check box.
Verify the Search result.
select a video from search result and verify the layout, hide/show some comments and Verify on web portal.
16 | Poll Management
| Verify the layout of Poll Management screen. | 4
Verify Search functionality for video.
Verify the Search result and search grid.
Select any video from Search result and verify the Details section.
Enter the details and click on Save button, verify on Web portal whether poll displayed for the video or not.
Verify Search functionality for Event
Verify the Search result and search grid.
Select any Event from Search result and verify the Details section.
Enter the details and click on Save button, verify on Web portal whether poll displayed for the event or not.
17 | Q&A Management
| Verify the layout of Q & A Management screen. | 3
Verify Search functionality for video.
Verify the Search result and search grid.
Select any video and verify the chat functionality for video also verify effect on Web Portal.
Verify the Hide comment functionality.
Verify Search functionality for Event.
Verify the Search result and search grid.
Select any Event and verify the chat functionality for video also verify effect on Web Portal.
Verify the Hide comment functionality.
18 | Account Management
Manage Account Tab :
| Verify the search functionality of Account Management. | 4
Verify the Search result and search grid.
Verify Activate/Inactivate button displayed.
Verify the functionality of Reset button.
Verify Account grid.
Verify the Navigation Panel
Verify the Edit functionality of Account Management
Manage User Tab :
| Verify the functionality to add new User. | 3
Verify clear button functionality under Add New User section.
Verify that newly added user is displayed in the manage user grid
Verify the layout of Manage User grid.
Verify that First name, last name and Email is hyperlink and redirected to Edit User.
Verify the Edit user functionality.
Verify the Delete user functionality.
Verify the Reset Password functionality.
Verify the Activate/Inactivate buttons functionality.
Verify the Upload User functionality.
Verify the functionality of "Back" button
Upload users tab
| Verify the functionality of "Download template". | 4
Verify the functionality of "bulk upload users"
Verify the uploaded users grid.
Verify the functionality of "Back" button
Add Individual Purchase Tab :
| Verify the Account Name | 4
Verify the search functionality for Video/Event
Verify search result and Search result grid.
Select a video from search result and Verify the functionality of "Add content" buttnon
verify the 'Purchase Content' grid.
Verify delete functionality of 'Purchase Content grid'.
Verify the functionality of "Save" button
Verify the functionality of "Cancel" button.
Verify integration with webportal
Create Access Tab :
| Verify the Account Name | 5
Verify the functionality of select channel section
Verify the Channel Catalogue Access grid.
Verify the default duration when user selects option from Type column.
Verify the functionaity of providing access to premium channel
Verify the functionality of "Save" button
Verify the functionality of "cancel" button
Verify integration with webportal
Access Details Tab :
| Verify the Account Name | 3
Channel Grid : - Verify the Layout. - Verify activate/Inactivate functionality. - Verify Edit functionality. - Verify Delete functionality.
Purchased Items Grid : - Verify the Layout. - Verify activate/Inactivate functionality. - Verify Edit functionality. - Verify Delete functionality.
Individual subscription page
| Verify the Account Name | 4
Channel Grid : - Verify the columns in the grid - Verify the functionality of Update channel, Update Catalogue and Access to column - Verify the functionality of History button - Verify the functionality of "Submit" button - Verify the functionality of "Cancel" button - Verify integration with WebPortal
19 | External Access
Create Tab :
| Verify the inline error message is displayed or not. | 3
Verify the functionality of Reset button.
Verify the functionality to create a external user.
Verify that username password is received on registered email address.
Verify that create user details is displayed on Manage grid.
Verify the received username and password is correct by logging on external user site.
Verify Only those Tab is displayed whose access is given to the user at the time of creation.
Verify the Logout functionality of external user site.
Manage Tab :
| Verify the search and Reset functionality. | 4
Verfiy the columns of grid.
Verfiy the Activate/Inactivate functionality.
After Inactivating, Verfiy user is allowed to login or not. User should not be allowed to login.
Verfiy reset password functionality.
Verify mail is recieved with new password on registered email address.
Verfiy that new password is valid by login on External user site.
Verfiy the Edit functiolaity.
Verify Email address field is disabled or not, in Edit mode.
Verfiy the Delete functiolaity.
After Deleting, Verfiy user is allowed to login or not. User should not be allowed to login.
226.5
Note on G13: Author: Integration with Webportal Assert is pending

## Web Portal
S. No. | Web Portal Functionalities
1 | Login | Estimated No. of Days | Allocated Date Slot | Verification Points | Total No. of Asserts | Constraints (If any) | Verification Points Reviewed By | Person Working on Test Script | Status | Verification of Script Execution on Platform / Browser | Comments (if any)
| Verify Login on Web Portal for Individual user(Without login / Visitor ). | 4
Verify Login on Web Portal for Individual user( Registered User ).
| Verify Login on Web Portal for Individual user( Member ). | [10 empty] | Not Started
| Verify Login on Web Portal for Individual user( IET Staff ). | [10 empty] | In Progress
| Verify Login on Web Portal for Individual user( Student ). | [10 empty] | Partially Completed
| Verify Login on Web Portal for Corporate user (IP only). | [10 empty] | On Hold
| Verify Login on Web Portal for Corporate user (JISC only). | [10 empty] | Completed
Verify Login on Web Portal for Corporate user (Username/password).
Verify Login on Web Portal for Corporate Admin user (Username/password).
Verify Login on Web Portal for Institution user (IP only).
Verify Login on Web Portal for Institution user (JISC only).
Verify Login on Web Portal for Institution user (Username/password).
Verify Login on Web Portal for Institution Admin user (Username/password).
Verify the 'Remember Me' functionality.
Verify the layout of the login screen.
Verify 'Other IET Websites' link on header bar on Login Screen.
Verify 'Contact' link on header bar on Login Screen.
Verify 'Forgot Password' link on Login Screen.
Verify the functionality on concurrent user logins.
Verify My IET menu for Admin, Normal ,IP Based and Individual user.
Verify the logout functionality.
2 | Individual registration
| Verify Link (Not registered with THE IET? Register here) on the login page. | 3 | W2 [20th July - 24th July] | Non IET Member Registration: 1.Validating all the mandatory fields on registration page 2.Validating Password and confirm password matching 3.Validating emaid id and confirm email id matching 4.Successfull registration banner message 5.Existing user name verification by clicking on 'Check User' button 6.Existing user name verification by clicking on 'Continue' button 7.Existing Emai Address verification. 8.Invalid Email Address verification 9.Password format validation 10.Verifying username after registration on home page IET Member Registration: 1.Validating all the mandatory fields on registration page 2.Validating Password and confirm password matching 3.Validating emaid id and confirm email id matching 4.Successfull registration banner message 5.Existing Membership ID verification 6.Existing user name verification 7.Existing Emai Address verification. 8.Invalid Email Address verification 9.Password format validation 10.Verifying username after registration on home page 11.Verifing the Date of Birth field validation | 33 |  |  | Babban | Partially Completed | IE11, Chrome & Firefox | IET member registration- 1.Email address matching validation is not working 2.Date of Birth validation on registration page
Verify create an IET web account for YES.
Verify create an IET web account for NO.
Verify the registration page.
3 | Terms and conditions
| Verify Terms & Condition page on New User Registration. [All user type] | 4
Verify the layout of the 'Terms & Condition' page [All user type]
Verify the navigation flow functionality from the T&C page [All user type]
Verify the Terms and Condition Link on the footer section [All user type]
4 | Change password
| Verify the functionality of change password | 1.5
5 | Access Control funtionality for different users
| Verify Subscription Access of Free, Subscribed and Premium Videos on Web Portal for Individual user ( Registered User ). | 5
Verify Subscription Access of Free, Subscribed and Premium Videos on Web Portal for Individual user ( Member ).
Verify Subscription Access of Free, Subscribed and Premium Videos on Web Portal for Individual user ( IET Staff ).
Verify Subscription Access of Free, Subscribed and Premium Videos on Web Portal for Individual user ( Student ).
Verify Subscription Access of Free, Subscribed and Premium Videos on Web Portal for Corporate user (IP only).
Verify Subscription Access of Free, Subscribed and Premium Videos on Web Portal for Corporate user (JISC only).
Verify Subscription Access of Free, Subscribed and Premium Videos on Web Portal for Corporate user (Username/password).
Verify Subscription Access of Free, Subscribed and Premium Videos on Web Portal for Corporate Admin user (Username/password).
Verify Subscription Access of Free, Subscribed and Premium Videos on Web Portal for Institution user (IP only).
Verify Subscription Access of Free, Subscribed and Premium Videos on Web Portal for Institution user (JISC only).
Verify Subscription Access of Free, Subscribed and Premium Videos on Web Portal for Institution user (Username/password).
Verify Subscription Access of Free, Subscribed and Premium Videos on Web Portal for Institution Admin user (Username/password).
6 | Channel Landing page
| Click Channels menu on Home Page. | NA [Already covered in admin portal]
Verify different channels under different category.
Click on any channel.
Verify Channel landing page.
7 | Forgotten password
| Verify the functionality of forgotten password | 3 | W1 [13th July - 17th July] | i. User is able to click on 'Forgot Password link' ii. User is able to fill the details into 'Request Form' iii. User is not able to proceed by clicking on continue button without entering captcha details |  | i. There is a 'Recaptcha' present on 'Request username / password reset' form which can't be automated ii. As understood by the manual testing team, the forgotten password email gets generated by schedular and thus we can't anticipate the time on which we will get the forgotten password mail and thus can't be verified considering this constraint | Rucha | Amit | Completed
Back to Login functionality
Verify the confirmation Email
8 | Home page - top bar
| Verify the functionality "Other IET Website" dropdown | 3 | W1 [13th July - 17th July] | i. Verify all the Elements are displayed or not which are present under 'Other IET Website' dropdown also verify status of each link ii. Verify buy channel button display and status iii. Verify login link URL after clicking on 'Welcome: please login" link also verify presence of contact button on header iv. Verify IET logo presence and status v. Verify banner display |  | No Constraint | Rucha | Babban | Completed
Verify the functionality buy channel buttons
Verify the functionality "Welcome: please login" link
Verify the functionality of the "IET Tv" logo
Verify the functionality "Ad banners"
9 | Buy channel
| Verify the Channels displayed in the buy channel page | 7
Verify the checkout functionality after selecting a channel catalog
Verify the purchase flow functionality
10 | Home page
| Verify the "home carousel" videos | 5
Verify the functionality of "Channel name" below the video in home carousel
Verify the functionality of the "Video name" below the video in home carousel
Verify the navigation buttons and dots in the "home carousel"
Verify the "Most popular" section
Verify the "Forthcoming" section
Verify the "Latest" section
11 | Search section
| Verify the functionlaity of the "All" button | 5
Verify the functionality of the search textbox
Verify the functionality of the "Calendar"
Verify the functionality of the "search" button
12 | Search results page
| Verify the functionality of pagination bar | 7 |  | Verify the functionality of "Search results" displayed
Verify the functionality of sort by dropdown
Verify the functionality of search facets displayed.
Verify the functionality of "Search results" displayed
13 | Help Dropdown
| Click the functionality of links under "IET Tv help". | 4 | W4 [4th August - 14th August]
Click the functionality of links under "Account types".
Verify the contents in the "Help" pages
Click the functionality of image in the help page
Play the functionality video in the help page
14 | Services dropdown
| Click the functionality of link in the services dropdown | 4
Verify the contents in the service page
Click the functionality of image in the service page
Play the functionality video in the service page
15 | Most popular section
| Click the "Video" in the most popular section | 3
Click the "Video name" in the most popular section
Click the "Channel name" in the most popular section
Click on "View all" link [Verify with Marklogic]
16 | Forthcoming section
| Click the "Video" in the Forthcoming section | 3
Click the "Video name" in the Forthcoming section
Click the "Channel name" in the Forthcoming section
Click on "View all" link [Verify with Marklogic]
17 | Latest section
| Click the "Video" in the Latest section | 3
Click the "Video name" in the Latest section
Click the "Channel name" in the Latest section
Click on "View all" link [Verify with Marklogic]
18 | Bottom Bar
| Verify the "Back to top" link above bottom bar | 3 | W2 [20th July - 24th July] | 1. Scroll Down and Verify Back to top element is present or not 2. Click on Back to top and verify Back to top functionality is working 3. Verify 'My community' icon presence and status 4. Verify 'About the IET' links presence and status 5. Verify 'IET Tv help' links presence and status 6. Verify 'Other IET Websites' links presence and status 7. Verify 'Cookies, Privacy statement', 'accessibility', 'Legal notices' and 'T&C' links presence and status |  | No | Rucha | Amit | Completed | IE11, Chrome & Firefox
Verify the "My community" links and icons
Verify the functionlaity of links in the "About the IET" in bottom bar
Verify the functionlaity of links in the "IET tv help" in bottom bar
Verify the functionlaity of links in the "IET tv account types" in bottom bar
Verify the functionlaity of links in the "Other IET Websites" in bottom bar
Verify the functionlaity of links Cookies, Privacy statement, accessibility, Legal notices, T&C
19 | Video landing page
| Verify the functionality of play button of video. | 5
Verify the functionality of speaker "view bio" link
Verify the functionality of "Like/Dislike" icon
Verify the functionality of "Download" button
Verify the functionality of "Channel name"
Verify the functionality of "Keywords"
Verify the functionality of "Attachments"
Verify the functionality of comments section
Verify the functionality of sponser image.
Verify the functionalitu of videos available in "Related videos" section
Verify the functionality of "Related content" link
Verify the functionality of "See also" link
Verify the functionality of "Embed" icon
20 | Event Landing Page
| Verify the layout of Event Landing Page. | 4
Verify the video loaded in the player area on Event landing page.
Verify different days of week are appearing as tabs.
Verify videos are appearing under days for which there is a video associated.
21 | User management- User
| Verify the functionality of Search users section | 4
Verify the functionality of "Manage users" section
Verify the functionality of "Activate selected users" and "Inactivate selected users" buttons
Verify the functionality of "Add users".
Verify the functionality of "Logo" upload
22 | User generated content
| Verify the functionality of "Upload content" | 3
Verify the functionality of "Status" tab
23 | Series Landing Page
| Verify the video loaded in the player area on Series landing page. | 5
Verify the embed button, views, video date, name of the series, like/dislike on Series landing page.
Verify the abstract on Series landing page.
Verify 20 videos are appearing on a single page of Series landing page.
Validate the pagination on Series landing page.
Validate the Sort By functionality on Series landing page.
Verify the related videos appearing on Series landing page.
24 | My IET: My IET TV
| Verify the two tabs 1. Subscriptions 2. Purchased Content appearing on My IET TV page. | 7
Verify whether Subscription tab is default tab.
Verify whether the correct subscriptions are appearing on Subscriptions tab in a grid.
Verify whether the subscribed channels are appearing as links
Validate whether the subscribed channels which should appear as links are navigating to correct channel landing page.
Validate the functionality of Back button on Subscriptions tab.
Validate the functionality of Turn Off Notifications checkbox on Subscriptions tab.
Verify whether the correct subscriptions are appearing on Purchased Content tab in a grid.
Validate the functionality of Back button on Purchased Content tab.
Validate the functionality of Turn Off Notifications checkbox on Purchased Content tab.
25 | My IET: MARC records
| Verify the layout of MARC records landing page. | 7
Verify the functionality of Download all button in 'All Records' section.
Verify the functionality of Download updates button in 'Updated Records' section.
26 | My IET: Access Report Dashboard
| Verify the different tabs on Access Report Dashboard landing page: 1. Select User 2. Select Date 3. Select Activity 4. Select Device/Channel 5. Select Type of Video 6. Select Video | 5
Verify whether 'Select User' tab is default tab.
Verify the layout of all the tabs.
Verify the functionality of Auto-suggest text box on 'Select User' tab.
Verify the functionality of dropdown when user has selected 'Date Range' radio button on 'Select Date' tab.
Verify the functionality of date picker when user has selected 'From & To Date' radio button on 'Select Date' tab.
Verify the functionality of dropdown on 'Select Activity' tab.
Verify the functionality of dropdown on 'Select Device/Channel' tab.
Verify the functionality of dropdown on 'Select Type of Video' tab.
Verify the functionality of Auto-suggest text box on 'Select Video' tab.
Verify the functionality of Back, Continue, Generate Report and Reset buttons on all the tabs.
Verify the generated report section.
107.5
Note on B89: Author: Exact image verification is pending

## Assumption
Assumptions
1. This estimation is only for Windows based browsers [IE10, IE11, Firefox(Latest), Chrome
2. This estimation doesn't include IE9, Safari (Mac OS) and Mobile browser,
3. Web application is up and running at the time of test execution/test script preparation. Downtime is not considered in this estimation
4. Verification points are available for each test scenario before start of actual test scripting
Technical Limitation
1. Investigation will be required for report verification (ex. Bar chart Report image) if needs to be automated
2. Investigation will be required for flash video play verification & download verfication [Webportal - 19]

## Sheet1
Sr. No. | IET TV Web Portal Module |  | Status | Estimated Start Date | Estimated Date of Completion | Demo Conducted | Comments (if any)
1 | Forgotten Password |  | Completed | 13th July 2015 | 17th July 2015 | No
2 | Home Page - Top Bar
3 | Bottom Bar |  | Completed | 20th July 2015 | 24th July 2015 | No | Individual Registration – Member is ‘On Hold’ due to an Issue. Same has been logged in SmartBear [ID: 3260073 ]
| Individual Registration | Non Member | Completed
|  | Member | On Hold
Sr. No. | IET TV Admin Portal Module |  | Status | Estimated Start Date | Estimated Date of Completion | Demo Conducted For Completed Modules | Comments (if any)
1 | Category Management |  | In Progress | 27th July 2015 | 3rd August 2015 | NA

## Bugs
JIRA ID | SmartBear ID | Description | Impact on Automation | Reported To | Status
TB-167 | 3272408 | IET Member Registration - User is allowed to register successfully, even Email and Confirm Email do not match while registration process for IET Member user. | Not able to write test case to verify Email address matching functionality. | Ujjwal and Amar | Not Resolved
TB-204 | 3294201 | Admin Portal-Category management - Multiple categories having same position |  | Ujjwal and Amar | Not Resolved
TB-205 | 3283356 | Admin Portal - Channel Management : Radio buttons under 'Access Type' are disabled, even user has selected 'Channel Type' as 'Standard'. | Not able to write test that include Access Type functionalities | Ujjwal and Amar | Not Resolved
TB-206 | 3294188 | Admin Portal - Channel Management - Create Channel - User not able to select Pricing Type after creating a channel with 'Channel type' as other than Standard. | Not able to write test case to edit channel. | Ujjwal and Amar | Not Resolved
TB-200 | 3300370 | Bug 1 : Caret direction of 'Services' menu is not changed to upward. Bug 2 : Label for displaying character count is not consistent in 'Content Area' editor. Bug 3 : In edit mode, Edit Icon is not displayed for Media container (if media container contains video) (In IE Browser) Bug 4 : If media container contains video then after opening either 'Title Area' editor or 'Content Area' editor, it gets overlapped with media containers. (In Firefox and IE Browser) | 1. Not able to write CMS tests for IE and Firefox browser. 2. To check character count functionality for content area editor is remaining. 3. To check caret direction of service menu is remaining. | Ujjwal and Amar | Not Resolved
TB-208 | 3302081 | Admin Portal - Regional Access: User is allowed to create multiple Region with same name. |  | Ujjwal and Amar | Not Resolved
TB-209 | 3303884 | Web Portal - Regional Access: Integration of Regional Access with Webportal is not working | Not able to test Region impact on WebPortal | Ujjwal and Amar | Not Resolved
TB-207 | 3302079 | User is not allowed to edit Region. | Not able to test the Edit region functionality | Ujjwal and Amar | Not Resolved

## Sheet2
Sr.no | Module Name
Video Management
| Following points are not covered for Standard video: | Following Follow:
| Create Free video | Create Free video with Copyright Authorisation, Different Permissions,Record Publish and final publish
| Create Premium video | Create Premium video with Add Copyright,Event, FTP Server,Final Publish and add Expiry Date
| Create video with show countdown | Create Subscription video, Keywords,Attachment(Activate and inactivate),Sponsor,Speakers
| Create video with Promo Video | Create video with Promo Video
| Create video with Promo Image | Create video with Promo Image
| Create video with Default Image | Create video with Default Image
Create video with Location Details
Create video with Subtitles and Transcripts
Create video with Syndication
Create video with Adverts
Create video with Clients
Create video with adding Production Info
Create video as Live Video
Create video with Hide Record
Following points are not covered for Promotional video:
Create video with FTP Server
Create video with Expiry Date